## Home Page
LYROVO
Version No:Chrome Version 121.0.6167.185 |  |  | Tested By:Swathy Krishna M
Verified By:Rakhi |  |  | Date:18/04/2024
LYROVO HOME PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
LY_LP_01 | Verify that the lyrovo page is launching correctly. | 1.Open lyrovo homepage | https://www.lyrovo.com/ | Lyrovo homepage should launch | Lyrovo homepage is opening | PASS
LY_LP_02 | Check whether the lyrovo homepage opens by clicking on lyrovo logo | 1.Open lyrovo homepage 2.Click on lyrovo logo | https://www.lyrovo.com/ | Lyrovo homepage should open by clicking on lyrovo logo | Lyrovo homepage is opening by clicking on lyrovo logo | PASS
LY_LP_03 | Ensure that lyrovo facebook profile opens by clicking on like us link | 1.Open lyrovo homepage 2.Click on like us link | https://www.lyrovo.com/ | Lyrovo facebook profile should open by clicking on like us link | Lyrovo facebook page is not opening | FAIL
LY_LP_04 | Check whether proper message comes when other values except alphabets are typed in search field | 1.Open lyrovo homepage 2.Write input in search field 3.Press enter key | 678 | Message should show "YOUR SEARCH FOR "678" DID NOT YIELD ANY RESULTS" | Message shows "YOUR SEARCH FOR "678" DID NOT YIELD ANY RESULTS" | PASS
LY_LP_05 | Check whether message that comes when non alphabetical values are typed in search field is properly aligned | 1.Open lyrovo homepage 2.Write input in search field 3.Press enter key | 6780 | Message alignment should be proper | Message alignment is not proper | FAIL
LY_LP_06 | Check whether the dropdown appears when hovered on categories link | 1.Open the lyrovo page 2.Hover on categories link | https://www.lyrovo.com/ | Categories dropdown list should open by hovering on categories link | Categories dropdown list is opening | PASS
LY_LP_07 | Verify that the catelog link navigates same as categories link | 1.Open the lyrovo page 2.Click on categories link 3.Click on catelog link | https://www.lyrovo.com/ | Categories link should include every products | Both links contents are same | FAIL
LY_LP_08 | Check whether the dropdown appears when hovered on support link | 1.Open the lyrovo page 2.Hover on support link | https://www.lyrovo.com/ | Dropdown list should open by hovering on support link | Dropdown list is opening | PASS
LY_LP_09 | Check whether the homepage opens when the home link is clicked | 1.Open the lyrovo page 2.Click on home link | https://www.lyrovo.com/ | Lyrovo homepage should open by clicking on home link | Homepage is opening by clicking on home link | PASS
LY_LP_10 | Check whether the collections page opens when the Catelog link is clicked | 1.Open the lyrovo page 2.Click on catelog link | https://www.lyrovo.com/ | Collections page should open by clicking on catelog link | Collection link is opening by clicking on catelog link | PASS
LY_LP_11 | Check whether the contact page opens when the contact link is clicked | 1.Open the lyrovo page 2.Click on contact link | https://www.lyrovo.com/ | Contact page should open by clicking on contact link | Contact page is opening by clicking on contact link | PASS
LY_LP_12 | Check whether the tracking page opens when the track your order link is clicked | 1.Open the lyrovo page 2.Click on track your order link | https://www.lyrovo.com/ | Tracking page should open by clicking on track your order link | Tracking page is opening by clicking on track your order link | PASS
LY_LP_13 | Check whether the About us opens when the about us link is clicked | 1.Open the lyrovo page 2.Click on about us link | https://www.lyrovo.com/ | About us page should open by clicking on about us link | About us is opening by clicking on about us link | PASS
LY_LP_14 | Check whether the Warranty activation page opens when thewarranty activation link is clicked | 1.Open the lyrovo page 2.Click on warranty activation link | https://www.lyrovo.com/ | Warranty page should open by clicking on warranty activation link | Warranty page is opening by clicking on warranty activation link | PASS
LY_LP_15 | Verify that the cart link is working | 1.Open the lyrovo page 2.Click on cart link | https://www.lyrovo.com/ | Cart section should open by clicking on cart link | Cart section is opening | PASS
LY_LP_16 | Check whether the wishlist page opens by clicking wishlist link | 1.Open the lyrovo page 2.Click on wishlist link | https://www.lyrovo.com/ | Wishlist page should open by clicking on wishlist link | Wishlist page is not opening | FAIL
LY_LP_17 | Verify that login page is opening by clicking on login link | 1.Open the lyrovo page 2.Click on login link | https://www.lyrovo.com/ | Login page should open by clicking on login link | Login page is opening | PASS
LY_LP_18 | Verify that the Register page is opening by clicking on register link | 1.Open the lyrovo page 2.Click on login link | https://www.lyrovo.com/ | Register page should open by clicking on register link | Register link is opening | PASS
LY_LP_19 | Ensure that my account link appears after logging in | 1.Open the lyrovo page 2.Click on login link 3.Write input in email id 4.Write input in password 5.Click on login button | 95mswathi@gmail.com S********* | My account link should appear only after logging in | My account link appears without logging in | FAIL
LY_LP_20 | Check whether scroll left and right icon are properly wrapped | 1.Open the lyrovo page | https://www.lyrovo.com/ | Scroll left and right icons should wrap at the edges of the image | Scroll left and right icon are not wrapped properly | FAIL
LY_LP_21 | Check whether scroll left and right icon are not overlapping on contents | 1.Open the lyrovo page | https://www.lyrovo.com/ | Scroll left and right icons should not overlap over the buttons | Scroll left and right icon are overlapping over buttons | FAIL
LY_LP_22 | Verify that images uploaded as links are not repeating | 1.Open the lyrovo page | https://www.lyrovo.com/ | Images given as links should not repeat | Some of the images are repeating | FAIL
LY_LP_23 | Verify that third image link navigates to corresponding buying pages of the given product in the images | 1.Open the lyrovo page 2.Click third image link | https://www.lyrovo.com/ | Third image link should navigate to corresponding buying pages of the product given in the images | Third image navigates to homepage | FAIL
LY_LP_24 | Verify that the image link under car and motorbike navigates to its corresponding page | 1.Open the lyrovo page 2.Click car and motorbike image link | https://www.lyrovo.com/ | It should navigate to products page that comes under car and motorbike category | Its navigating to corresponding pages | PASS
LY_LP_25 | Verify that the image link under home and kitchen navigates to its corresponding page | 1.Open the lyrovo page 2.Click home and kitchen image link | https://www.lyrovo.com/ | It should navigate to products page that comes under home and kitchen category | Its navigating to corresponding pages | PASS
LY_LP_26 | Verify that the image link under luggages and bags navigates to its corresponding page | 1.Open the lyrovo page 2.Click luggage and bags image link | https://www.lyrovo.com/ | It should navigate to products page that comes under luggage and bags category | Its navigating to corresponding pages | PASS
LY_LP_27 | Check whether scroll up icon moves page to top of homepage | 1.Open the lyrovo page 2.Scroll to the bottom 3.Click on scroll up icon | https://www.lyrovo.com/ | Scroll up icon should move to the top of the homepage when clicked | Page moves to the top of the homepage by clicking on scroll up icon | PASS
LY_LP_28 | Check whether products which are wishlisted moves to wishlist page before logging in | 1.Open the lyrovo page 2.Select an item to add on wishlist by clicking on love icon | https://www.lyrovo.com/ | Products should add to wishlist before logging in | No products are in wishlist | FAIL
LY_LP_29 | Check whether the image links under product are working | 1.Open the lyrovo page 2.Click on image links under product | https://www.lyrovo.com/ | All image links under product should work | All image links under product are working | PASS
LY_LP_30 | Check whether the buynow button for portable foot pump works | 1.Open the lyrovo page 2.Click on buy now button | https://www.lyrovo.com/ | It should work by clicking on buy now button | Its working when we clicks buy now button | PASS
LY_LP_31 | Verify that image link of portable foot pump works | 1.Open the lyrovo page 2.Click on image link of portable foot pump | https://www.lyrovo.com/ | Image link should work by cllicking on the image of portable foot pump | Image link is working | PASS
LY_LP_32 | Ensure that scroll left and right icon under trending now is properly wrapped | 1.Open the lyrovo page | https://www.lyrovo.com/ | Scroll left and right icon should not overlap over images | Scroll left and right icon are overlapping over images | FAIL
LY_LP_33 | Verify that all image links under trending now works | 1.Open the lyrovo page 2.Click on all image links under trending now | https://www.lyrovo.com/ | Image links under trending now should work properly | Image links under trending now are working | PASS
LY_LP_34 | Check whether the instagram link works | 1.Open the lyrovo page 2.Click on view gallery | https://www.lyrovo.com/ | Instagram link should navigate to lyrovo instagram profile page | Its navigating to its instagram page | PASS
LY_LP_35 | Ensure correct title is given for instagram link button | 1.Open the lyrovo page | https://www.lyrovo.com/ | Proper title should be given to the button for instagram navigation | View gallery is written on button which is misleading | FAIL
LY_LP_36 | Check whether the information title on the footer of page has any contents | 1.Open the lyrovo page | https://www.lyrovo.com/ | Information title should not be there | Information title has no submodules or contents | FAIL
LY_LP_37 | Check whether the submodules under footer menu on footer of page is repeating | 1.Open the lyrovo page | https://www.lyrovo.com/ | Footer menu should not be there | Submodules under footermenu are repeating | FAIL
LY_LP_38 | Check whether the submodules under our policies are working | 1.Open the lyrovo page 2.Click on Privacy Policy 3.Click on Refund policy 4.Click on Terms of Service 5.Click on Warranty Activation | https://www.lyrovo.com/ | Submodules under our policies should work | Submodules under our policies are working | PASS
LY_LP_39 | Check whether icons under follow us are working | 1.Open the lyrovo page 2.Click on facebook icon 3.Click on instagram icon 4.Click on pinterest icon 5.Click on youtube icon | https://www.lyrovo.com/ | All icons under follow us should work | All icons under follow us are working | PASS
LY_LP_40 | Check whether the chat assistant works | 1.Open the lyrovo page 2.Click on chat | https://www.lyrovo.com/ | Chat assistant should work by clicking on chat | Chat assistant is working | PASS
LY_LP_41 | Check whether the newsletter field comes after logging in | 1.Open the lyrovo page 2.Click on login link 3.Write input in email id 4.Write input in password 5.Click on login button | 95mswathi@gmail.com S********* | Newsletter field should be a checkbox after logging in | Newsletter field is present before logging in | FAIL
LY_LP_42 | Check whether the submodule privacy policy under support is working | 1.Open the lyrovo page 2.Click on support link under shops section 3.Click on privacy policy link | https://www.lyrovo.com/ | Privacy policy link should open privacy policy page | Privacy policy link showing 404 error | FAIL
LY_LP_43 | Verify that submodules under shops work | 1.Open the lyrovo page 2.Click on Home 3.Click on Categories 4.Click on Catalog 5.Click on Contact 6.Click on Support 7.Click on Track Your Order 8.Click on About Us 9.Click on Warranty Activation | https://www.lyrovo.com/ | All submodules under shops should work | All submodules under shops are working | PASS
LY_LP_44 | Check whether like us facebook link is repeating | 1.Open the lyrovo page | https://www.lyrovo.com/ | Like us facebook should not repeat | Unwanted like us facebook text is written on footer of page | FAIL

## Login Page
LYROVO
Version No:Chrome Version 121.0.6167.185 |  |  | Tested By:Swathy Krishna M
Verified By:Rakhi |  |  | Date:18/04/2024
LOGIN PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
LP_LO_01 | Check whether the email address field is working | 1.Open the lyrovo page 2.Click on login link 3.Click on email address field | https://www.lyrovo.com/ | Email address field should be active | Email address field is active by clicking on it | PASS
LP_LO_02 | Check whether the password field is working | 1.Open the lyrovo page 2.Click on login link 3.Click on password field | https://www.lyrovo.com/ | Password field should be active | Password field is active by clicking on it | PASS
LP_LO_03 | Verify that the login modal opens by clicking on login link | 1.Open the lyrovo page 2.Click on login link | https://www.lyrovo.com/ | Login modal should open by blocking other contents of site | Login modal is opening by clicking on login link | PASS
LP_LO_04 | Check whether the login modal closes when close link is clicked | 1.Open the lyrovo page 2.Click on login link 3.Click close link | https://www.lyrovo.com/ | Login modal should close by clicking on close link | Login modal closes by clicking on close link | PASS
LP_LO_05 | Check whether the login button hover active colour fill is black | 1.Open the lyrovo page 2.Click on login link 3.Place mouse on login button | https://www.lyrovo.com/ | Login button hover active colour fill should be black | Login button hover active colour fill is black | PASS
LP_LO_06 | Check whether the create an account button hover active colour fill is black | 1.Open the lyrovo page 2.Click on login link 3.Place mouse on create an account button | https://www.lyrovo.com/ | Create an account button hover active colour fill should be black | Create an account button hover active colour fill is white | FAIL
LP_LO_07 | Verfiy that forgot your password link hover is active | 1.Open the lyrovo page 2.Click on login link 3.Place mouse on forgot your password link | https://www.lyrovo.com/ | Forgot your password link hover should be active | Forgot your password hover is active | PASS
LP_LO_08 | Check whether the register page opens by clicking on create an account button | 1.Open the lyrovo page 2.Click on login link 3.Click on create an account button | https://www.lyrovo.com/ | Register page should open by clicking on create an account button | Register page is opening by clicking on create an account button | PASS
LP_LO_09 | Check whether the recover page opens by clicking on forgot your password link | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link | https://www.lyrovo.com/ | Recover page should open by clicking on forgot your password link | Recover page is opening by clicking on forgot your password link | PASS
LP_LO_10 | Check whether an alert message shows by clicking on login button without inputs in email and password field | 1.Open the lyrovo page 2.Click on login link 3.Click on login button | https://www.lyrovo.com/ | An alert message showing fill the above fields should show | No alert message is showing | FAIL
LP_LO_11 | Check whether captcha verification page shows by clicking on login button without inputs in email and password field | 1.Open the lyrovo page 2.Click on login link 3.Click on login button | https://www.lyrovo.com/ | Captcha verification page showing I'm not a robot checkbox should open | Captcha verifiaction page is opening | PASS
LP_LO_12 | Verify that site doesn’t allow when submit button in captcha verification page is clicked without selecting I'm not a robot checkbox | 1.Open the lyrovo page 2.Click on login link 3.Click on login button 4.Click on submit button | https://www.lyrovo.com/ | A text message showing "To continue, let us know you're not a robot.Your answer wasn't correct, please try again" should appear | A text message appears | PASS
LP_LO_13 | Verify that password eye icon is present next to password field | 1.Open the lyrovo page 2.Click on login link 3.Click on login button | https://www.lyrovo.com/ | Password eye icon field should be present | Password eye icon field is not present | FAIL
LP_LO_14 | Ensure that the password field input is hidden by default | 1.Open the lyrovo page 2.Click on login link 3.Write input in password field | https://www.lyrovo.com/ | Password field input should be hidden in default | Password field input is hidden by default | PASS
LP_LO_15 | Check whether the email address field accepts input without email format | 1.Open the lyrovo page 2.Click on login link 3.Write input in email address field 4.Press enter key | 1234 | Email address field should show a toast message containing "Please include an @ in the email address and a part following @ " | Email address field shows "Please include an @ in the email addres" | PASS
LP_LO_16 | Ensure that I'm not a robot is selected and submit button is clicked it has to verify and navigate to login page | 1.Open the lyrovo page 2.Click on login link 3.Click on login button 4.Select I'm not a robot checkbox 5.Click on submit button | https://www.lyrovo.com/ | Login page should open only after submit button is clicked and verification is done | Login page open only after verification | PASS
LP_LO_17 | Check whether the login page loads when email and password field doesnot match | 1.Open the lyrovo page 2.Click on login link 3.Write input in email address field 4.Write input in password field 5.Click on login button 6.Select I'm not a robot 7.Click on submit button | https://www.lyrovo.com/ | Login page should load when email and password field doesnot match | Login page opens when email and password field doesn’t match | PASS
LP_LO_18 | Verify that a toast message appears when an incomplete email address is inputted and password field is clicked | 1.Open the lyrovo page 2.Click on login link 3.Write input in email address field 4.Click on password field | 1234 | A toast message should appear when email field is incomplete and password field is clicked | Toast message is not showing | FAIL
LP_LO_19 | Check whether the email field character limit before "@" is 64 | 1.Open the lyrovo page 2.Click on login link 3.Write input in email address field | jdfhjsdfhdafjkafjkdfbjkadfbjkasdb34285678134#@@%#^#%^@%@$^@%%@$%%dabbhjsjbd | Email id field should restrict charcters after 64 | Email id field is not restricting | FAIL
LP_LO_20 | Check whether the email id field accepts space characters | 1.Open the lyrovo page 2.Click on login link 3.Write input in email address field 4.Press enter key | fghsd sjgds@gmail.com | Email id field should not accept space characters | Email id field is not accepting characters | PASS
LP_LO_21 | Ensure that the password field cursor is active when email id field is inputted and enter key is clicked | 1.Open the lyrovo page 2.Click on login link 3.Write input in email address field 4.Press enter key | 2323asfdf@gmail.com | Password field cursor should be active when enter key is clicked and email field is inputted | Login page loads when enter key is pressed | FAIL
LP_LO_22 | Check whether email field and password is completed before clicking on login button | 1.Open the lyrovo page 2.Click on login link 3.Click on email address field 4.Press enter key 4.Click on password field 5.Press enter key | https://www.lyrovo.com/ | An alert box showing Please enter the email and password should show | No alert box is shown | FAIL
LP_LO_23 | Check whether the Account page opens when email and password matches by clicking on login button | 1.Open the lyrovo page 2.Click on login link 3.Click on email address field 4.Press enter key 4.Click on password field 5.Press enter key 6.Click on login button 7.Select I'm not a robot checkbox 8.Click on submit button | 95mswath@gmail.com S********* | Account page should open by clicking on login button | Account page is opening | PASS
LP_LO_24 | Check whether toast message comes when incomplete password is written in recover page | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button | 1234 | Toast message showing incomplete email id should show | Toast message is showing | PASS
LP_LO_25 | Check whether homepage opens when cancel link is clicked in recover page | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Click on cancel button | https://www.lyrovo.com/ | Homepage should open by clicking on cancel button in recover page | Homepage is opening | PASS
LP_LO_26 | Check whether an alert box appears if email id does not exist | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button | swathi.m_95@yahoo.com | An alert box containing this email id doesnot exist should show | No alert box is shown | FAIL
LP_LO_27 | Verify that reset password link has send to the given email id | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button | swathi.m_95@yahoo.com | An email containing reset password link should be sent to the given email id | Reset password link is send | PASS
LP_LO_28 | Check whether the reset password link in the mail is working | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password | swathi.m_95@yahoo.com | Reset password page should open | Reset password page is opening | PASS
LP_LO_29 | Check whether the password field input entered is strong | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 8.Write input in password field 9.Press enter key | 123 | An text message should show this field must contain special characters,lowercase,uppercase,numerical and minimum 5 characters | Text message is shown | PASS
LP_LO_30 | Check whether the input in password field matches with confirm password field | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 8.Write input in password field 9.Press enter key 10.Write input in confirm password field 9.Click on submit button | SWAthi swathip | A text message should show | Text message is shown | PASS
LP_LO_31 | Verify that the password eye icon is present next to password field | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password |  | Password eye icon field should be present | No password eye icon is present | FAIL
LP_LO_32 | Verify that the password eye icon is present next to confirm password field | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password |  | Password eye icon field should be present | No password eye icon is present | FAIL
LP_LO_33 | Check whether the new password has been updated | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password field 4.Click on login button | 95mswath@gmail.com S***** | Password reset should be done | Password has been reset | PASS
LP_LO_34 | Verify that the password field input is hidden by default | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 8.Write input in password field | ssf | Password field input should be hidden in default | Password field input is hidden by default | PASS
LP_LO_35 | Verify that the confirm password field input is hidden by default | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 8.Write input in confirm password field | ghh | Password field input should be hidden in default | Password field input is hidden by default | PASS
LP_LO_36 | Check whether the login page opens when password has been reset | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 8.Write input in password field 9.Write input in password field 10.Click on submit button | S***** S***** | Login page should open | Account page is opening | FAIL
LP_LO_37 | Check whether the new password entered in reset password should not be same as current password | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 8.Write input in password field 9.Press enter key | S***** | A text message should show containing type a new password | Its not showing text message | FAIL
LP_LO_38 | Check whether password field and confirm password field is complete by pressing enter key | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 8.Write input in password field 9.Press enter key 10.Press enter key | S****** | A toast message should show containing please enter both fields | Its showing a toast message | PASS
LP_LO_39 | Check whether the reset password link in the mail has timeout | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 8.Open mail 9.Click on reset your password |  | Reset password link should have timeout | It has timeout | PASS
LP_LO_40 | Check whether the reset password accepts too many attempts | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 10.Repeat the steps 4 and 5 three times |  | Something went wrong page should show | Something went wrong page is opening | PASS
LP_LO_41 | Check whether the email id field input in login modal shows an alert when the mail id doesnot exist | 1.Open the lyrovo page 2.Click on login link 3.Click on email address field 4.Press enter key 4.Click on password field 5.Press enter key 6.Click on login button | swathi.m_95@yahoo.com S********* | An alert box showing this mail id doesnot exist should show | No alert box is shown | FAIL

## Registration
LYROVO
Version No:Chrome Version 121.0.6167.185 |  |  | Tested By:Swathy Krishna M
Verified By:Rakhi |  |  | Date:18/04/2024
REGISTRATION PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
LY_RP_01 | Check whether the first name field accepts only alphabetical characters | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key | 1234 | Toast message containing this field must contain only alphabetical characters should show | Toast message is not shown | FAIL
LY_RP_02 | Check whether the first name field accepts only minimum 5 characters | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key | swat | Toast message containing this field must have atleast 5 characters should show | Toast message is not shown | FAIL
LY_RP_03 | Check whether the first name field accepts maximum 15 characters | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key | khjhajsajgshjagshg | Toast message containing this field must have maximum 15 characters should show | Toast message is not shown | FAIL
LY_RP_04 | Verify that the first name field input first word is uppercase | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key | swathi | First name field should automatically convert first word to uppercase | First name field is not converting to uppercase | FAIL
LY_RP_05 | Verify that first name field accepts only one space character | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key | s m k | First name field should accept only one space character | First name field contains more than one space character | FAIL
LY_RP_06 | Verify that the first name field first character must not be a space character | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key | _swa | First name field first character should not be a space character | First name field accepts first character as space | FAIL
LY_RP_07 | Check whether cursor is moved to last name field if first name field is complete | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key | swathy | It should move to last name field | Its doesn’t move to last name field | FAIL
LY_RP_08 | Check whether blank first name field shows a message when cursor is placed in last name field | 1.Open the lyrovo page 2.Click on register link 3.Click on last name field |  | Toast message containing first name field cannot be empty should show | Toast message is not shown | FAIL
LY_RP_09 | Check whether the last name field accepts only alphabetical characters | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key | 712563 | Last name field should accept only alphabetical characters | Last name field accepts every type of characters | FAIL
LY_RP_10 | Check whether the last name field accepts only minimum 5 characters | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key | sahs | Last name should accept minimum 5 characters | Last name field accepts less than 5 characters | FAIL
LY_RP_11 | Check whether the last name field accepts maximum 15 characters | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key | jsbhjdgfghdhdgfgdsjfgsdhfgsdjfgsdgf | Last name field should accept characters upto 15 | Last name field has no limitation | FAIL
LY_RP_12 | Verify that the last name field input first word is uppercase | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key | swathi | Last name field should change first characeter to uppercase | Last name field doent change first characetr to uppercase | FAIL
LY_RP_13 | Verify that last name field accepts only one space character | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key | s k m | Last name field should accept only one space character | Last name field accept more than one space character | FAIL
LY_RP_14 | Verify that the last name field first character must not be a space character | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key | _swat | Last name field first character should not be a space character | Last name field character accepts first character as space | FAIL
LY_RP_15 | Check whether cursor is moved to your email address field if last name field is complete | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key | krishna | Cursor should move to email address field | Cursor doesn’t move to email address field | FAIL
LY_RP_16 | Check whether blank last name field shows a message when cursor is placed in your email address field | 1.Open the lyrovo page 2.Click on register link 3.Place cursor n email address field |  | Toast message should show when last name field is empty | Toast message is not shown | FAIL
LY_RP_17 | Check whether the email address field contain email format | 1.Open the lyrovo page 2.Click on register link 3.Write input in email address 4.Press enter key | sgdhgdhsg | A toast message showing incomplete email format should show | Toast message is shown | PASS
LY_RP_18 | Check whether blank your email address field shows a message | 1.Open the lyrovo page 2.Click on register link 3.Click on Create an account button |  | A text message showing email address cannot be blank should show | Text message is shown | PASS
LY_RP_19 | Check whether the email id entered exists | 1.Open the lyrovo page 2.Click on register link 3.Write input in email address field 4.Press enter key 5.Write input in password field 6.Click on create an account button | 95mswathi@gmail.com | A text message showing email id exist should show | Text message is shown | PASS
LY_RP_20 | Check whether the password field has password eye icon | 1.Open the lyrovo page 2.Click on register link |  | Password eye icon should be present next to password field | Password eye icon is not present | FAIL
LY_RP_21 | Check whether the password field input is hidden in default | 1.Open the lyrovo page 2.Click on register link 3.Write input in password field | cdfd | Password field should hide input | Password field doesn’t accept empty values | PASS
LY_RP_22 | Check whether your email address field does not accept space characters | 1.Open the lyrovo page 2.Click on register link 3.Write input in email address field 4.Press enter key | _swahi.m@gmail.com | Email address field should show a text message | Email address field shows a text message | PASS
LY_RP_23 | Check whether a text message appears when any of the fields are blank by clicking on create an account button | 1.Open the lyrovo page 2.Click on register link |  | Text message should show | Text message is shown | PASS
LY_RP_24 | Check whether a message comes when create an account button is clicked and then navigates to login page | 1.Open the lyrovo page 2.Click on register link 3.Write appropriate input in the fields |  | A message showing account created successfully should show and login page should open | No message is shown and my account page is opening | FAIL
LY_RP_25 | Check whether the mobile number field is present in register page | 1.Open the lyrovo page 2.Click on register link |  | Mobile number field should be present | Mobile number field is not present | FAIL
LY_RP_26 | Check whether the email verification code field is present | 1.Open the lyrovo page 2.Click on register link |  | Email verification field should be present | Email verification field is not present | FAIL
LY_RP_27 | Check whether confirm password field is present | 1.Open the lyrovo page 2.Click on register link |  | Confirm password field should be present | Confirm password field is not present | FAIL
LY_RP_28 | Verify that the email address and password is successfully created by logging in | 1.Open the lyrovo page 2.Click on register link 3.Write input in email address 4.Write input in password 5.Click on create an account button 6.Click on login link 7.Write input in email address 8.Write input in password 9.Click on login button | 95mswathi@gmail.com S***** | Account should be able to log in | Account logs in | PASS
LY_RP_29 | Check whether the blank password field shows a message | 1.Open the lyrovo page 2.Click on register link 3.Press enter key |  | Password field should not accept empty values | Password field doesn’t accept empty values | PASS

## UserProfile Page
LYROVO
Version No:Chrome Version 121.0.6167.185 |  |  | Tested By:Swathy Krishna M
Verified By:Rakhi |  |  | Date:18/04/2024
USER PROFILE AND CART PAGE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
LY_UP_01 | Check whether wishlist page opens by clicking on wishlist icon | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on wishlist icon | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Wishlist page should open | Wishlist page is not opening | FAIL
LY_UP_02 | Check whether user name appears as link next to logout link | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | User name should appear as link next to logout link | My account link is next to logout link | FAIL
LY_UP_03 | Check whether home page appears when logout link is clicked | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on logout link | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Homepage should appear with login link | Homepage is opening with login link | PASS
LY_UP_04 | Check whether cart modal appears when cart icon is clicked | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on cart icon | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Cart modal should appear | Cart modal is opening | PASS
LY_UP_05 | Check whether order history shows details of the orders | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Order history should be there | Order history is present | PASS
LY_UP_06 | Check whether addresses page opens when view addresses is clicked | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Addresses page should open | Addresses page is opening | PASS
LY_UP_07 | Check whether the account page appears when my account link is clicked | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on my account link | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Account page should open | Account page is opening | PASS
LY_UP_08 | Check whether the homepage appears without logging out and logout link stays | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on home link | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Homepage should appear with logout link | Homepage is opening with logout link | PASS
LY_UP_09 | Check whether the first name field accepts only alphabetical characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key | 123 | First name field should accept only alphabetical characters | First name field contains other characters | FAIL
LY_UP_10 | Check whether the first name field contains only one space characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key | Swathi Krishna m | First name field should accept only one space character | First name field contains other characters | FAIL
LY_UP_11 | Check whether the first name field accepts upto 15 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key | abjgsjdjasgdhasgdhgasdhgashdg | First name field should accept characters upto 15 | First name field contains more than 15 characters | FAIL
LY_UP_12 | Check whether the first name field first character is uppercase | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key | swathi | First name field should change first character to uppercase | First name field doesn’t change first character to uppercase | FAIL
LY_UP_13 | Check whether the first name field has no empty values | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key |  | First name field should not accept empty values | First name field contains empty value also | FAIL
LY_UP_14 | Check whether the first name field contain minimum 3 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key | sw | First name field should not accept less than 3 characters | First name field has no limit | FAIL
LY_UP_15 | Check whether the last name field accepts only alphabetical characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key | 123 | Last name field should accept only alphabetical characters | Last name field contains other characters | FAIL
LY_UP_16 | Check whether the last name field contains only one space characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key | Swathi Krishna m | Last name field should accept only one space character | Last name field contains other characters | FAIL
LY_UP_17 | Check whether the last name field accepts upto 15 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key | abjgsjdjasgdhasgdhgasdhgashdg | Last name field should accept characters upto 15 | Last name field contains more than 15 characters | FAIL
LY_UP_18 | Check whether the last name field first character is uppercase | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key | swathi | Last name field should change first character to uppercase | Last name field doesn’t change first character to uppercase | FAIL
LY_UP_19 | Check whether the last name field has no empty values | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key |  | Last name field should not accept empty values | Last name field contains empty value also | FAIL
LY_UP_20 | Check whether the last name field contain minimum 3 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key | sw | Last name field should not accept less than 3 characters | Last name field has no limit | FAIL
LY_UP_21 | Check whether the company field accepts upto 30 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in company field 8.Press enter key | hghgdhsdhfhsdfghjdghgdfhgsdhfgdshfghdsgfhjdsfhsdgfhsdgfhjgfgsdfgsdhgfjdsfhsdgfhsdgfhsgjfgsjgfhdsgf\dsgfhsg | Company field should accept characters only upto 30 | Company field has no limit | FAIL
LY_UP_22 | Verify that the company field contain numerical and alphabetical characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in company field 8.Press enter key | ___!#@#^&&* | Company field should conatin only numerical and alphabetical characters | Company field accepts every type of character | FAIL
LY_UP_23 | Ensure that company field accepts empty values also | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in company field 8.Press enter key |  | Company field should accept empty values | Company field accepts empty values | PASS
LY_UP_24 | Ensure that address2 field accepts empty values also | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address2 field 8.Press enter key |  | Address 2 field should accept empty values | Address 2 field accepts empty values | PASS
LY_UP_25 | Check whether the address1 field has no empty values | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address1 field 8.Press enter key |  | Address 1 field should not accept empty values | Address1 field accepts empty values | FAIL
LY_UP_26 | Verify that the address1 field contain numerical and alphabetical characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address1 field 8.Press enter key | ___!#@#^&&* | Address 1 field should contain only numerical ad alphabetical characters | Address 1 field accepts every type of characters | FAIL
LY_UP_27 | Verify that the address2 field contain numerical and alphabetical characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address 2 field 8.Press enter key | ___!#@#^&&* | Address 2 field should contain only numerical and alphabetical characters | Address 2 field accepts every type of characters | FAIL
LY_UP_28 | Check whether address1 field accepts upto 100 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address 1 field 8.Press enter key | jhajabjbhjbdjhadhasjdahsdsadasgdhgdhashdsagdsgdjsdgjsadjasgdjasfjagdfukWGHIOLFHEWBDHAHGDAUSJGBHAGDyyugGasgahsdgfyerugbruebvhrjebhjbvreburefbregvyhrevbyheryhegrvyrgveryy | Address 1 field should contain characters upto 100 | Address 1 field contain more than 100 characters | FAIL
LY_UP_29 | Check whether address2 field accepts upto 100 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address2 field 8.Press enter key | jhajabjbhjbdjhadhasjdahsdsadasgdhgdhashdsagdsgdjsdgjsadjasgdjasfjagdfukWGHIOLFHEWBDHAHGDAUSJGBHAGDyyugGasgahsdgfyerugbruebvhrjebhjbvreburefbregvyhrevbyheryhegrvyrgveryy | Address 2 field should contain characters upto 100 | Address2 field contain more than 100 characters | FAIL
LY_UP_30 | Check whether the city field accepts upto 20 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in city field 8.Press enter key | dhaghghagjaghagshgashdadashdghadghasdghagdagd | City field should accept characters upto 20 | City field accepts more than 20 characters | FAIL
LY_UP_31 | Verfiy that city field accepts only alphabetical characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in city field 8.Press enter key | 2367 | City field should accept only alphabetical characters | City field accepts every type of characters | FAIL
LY_UP_32 | Verify that the city field contains minimum 3 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in city field 8.Press enter key | as | City field should contain minimum 3 characters | City field accept less than 3 characters | FAIL
LY_UP_33 | Check whether the city field has no empty values | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in city field 8.Press enter key |  | City field should not accept empty values | City field accepts empty values | FAIL
LY_UP_34 | Ensure that country field dropdown is working | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Click on country field |  | Country field dropdown should work | Country field dropdown is working | PASS
LY_UP_35 | Check whether the default value in country is "---" | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address |  | Country field default value should be "---" | Country field default is not "---" | FAIL
LY_UP_36 | Check whether the province field appears when country field has country name values | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select india in country field | India | Province field should appear | Province field appears | PASS
LY_UP_37 | Verify that the province field updates prior to corresponding states of the selected country name | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select india in country field | India | Province field should update states prior to country field value | Province field updates states prior to country field values | PASS
LY_UP_38 | Check whether the default value in province is "---" | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select india in country field | India | Default value in province field should be "---" | No default value is present for province field | FAIL
LY_UP_39 | Ensure that province field dropdown is working | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select india in country field 8.Click on province field | India | Province field dropdown should work | Province field dropdown is working | PASS
LY_UP_40 | Verify that the country field has no empty values | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select "---" in country field | "---" | Country field should not accept empty values | Country field accepts empty values | FAIL
LY_UP_41 | Verify that the province field has no empty values | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select india in country field 8.Select "---" in province field | India ---- | Province field should not accept empty values | Province field accepts empty value | FAIL
LY_UP_42 | Verify that the postal code accepts only numerical characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in postal code field 8.Press enter key | hsdgshdgh | Postal code field should accept only numerical characters | Postal code field accepts every type of characters | FAIL
LY_UP_43 | Check whether the phone field accepts only numerical characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in phone number field 8.Press enter key | hsdgshdgh | Phone number field should accept only numerical characters | Phone number field accepts every type of characters | FAIL
LY_UP_44 | Check whether the phone field limit depends on country value | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select india in country value 8.Write input in phone field 9.Press enter key | India 131432545345346 | Phone field should accept only 10 numerical characters if country value is india | Phone field has no limit | FAIL
LY_UP_45 | Verify that set as default checkbox is working | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Check set as default checkbox |  | Set as default checkbox should written inputs as default in address page | Set as default checkbox is working | PASS
LY_UP_46 | Check whether cancel link is working | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Click on cancel link |  | It should navigate to account page | It navigates to account page | PASS
LY_UP_47 | Check whether address adding process stops when cancel link is clicked | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Click on cancel link |  | It should stop the address adding process | It stops the address adding process | PASS
LY_UP_48 | Check whether add address button is working | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write appropriate values in fields 8.Click on add address button | add address | Add address button should add inputted values to view addresses section in address page | Add address button is working | PASS
LY_UP_49 | Check whether the all fields are filled when add address button is clicked | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Write appropriate values in fields 6.Click on add address button 7.Write appropriate inputs in the fields 8.Press enter key | add address | A text message should appear containing all fields are mandatory without adding the address | Text containing only password and email address field is mandatory is showing | FAIL
LY_UP_50 | Check whether add new address button is working | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on add new address button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Empty value address page should open | Empty value address page opens | PASS
LY_UP_51 | Check whether return to account details link is working | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on return to account details link | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Account page should open | Account page is opening | PASS
LY_UP_52 | Check whether quantity spin box accepts only values above 1 in cart modal | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on cart icon 6.Click on down button in spin box |  | Spin box value should accept values above 1 | Spin box value accept negative and 0 numbers | FAIL
LY_UP_53 | Check whether cart page opens when cart button in cart modal is clicked when spin box field is negative | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on cart icon 6.Click on down button in spin box 7.Click on view cart button | -1 | Cart page should have empty cart item | Cart page is not working | FAIL
LY_UP_54 | Check whether items per page is working | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on catelog link 6.Select numbers in item per page | 12 | Item per page should show 12 products in the catelog page | Item per page is not working | FAIL

## Checkout and Payment
LYROVO
Version No:Chrome Version 121.0.6167.185 |  |  | Tested By:Swathy Krishna M
Verified By:Rakhi |  |  | Date:18/04/2024
CHECKOUT AND PAYMENT
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
LY_CP_01 | Check whether the dropdown in account section in checkout page is working | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Given email address should automatically fill in account section field and logout link should be present | Email address and logout link is present | PASS
LY_CP_02 | Check whether log out link in account section in checkout page is logging out of the account | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on logout link in account section | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Checkout without logging in page should open | Checkout with logging in page opens | PASS
LY_CP_03 | Check whether default address from address page is autofilled in first address radio button in ship to section | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Address from address page should autofill in default address radiobutton | Address from address page autofills | PASS
LY_CP_04 | Verify that if any of the input in address is wrong then checkout page shows it | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on Pay Now button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | An alert red text should appear and field border should be red | Red alert text is appearing and field border becomes red | PASS
LY_CP_05 | Verify that if any of the input in address is wrong then checkout page shows it and editting also can be done | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Delivery section should appear and ship to section should dissappear | Delivery section appears and ship to section dissappears | PASS
LY_CP_06 | Check whether the shipping charge is added if total amount is below ₹800 | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Shipping charge should add | Shipping charge does not add | FAIL
LY_CP_07 | Check whether the shipping charge is free if total amount is above/equal to ₹800 | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Shipping charge should be free | Shipping charge is free | PASS
LY_CP_08 | Check whether email me with news and offers checkbox can be selected | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Select email me with news and offers checkbox | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Selection of email me with news and offers should be done | Selects email me with news and offers checkbox | PASS
LY_CP_09 | Check whether the radio button in payment section can be selected only one at a time | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Select any of the radiobutton 10.Again try to select other radiobutton | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Only one radio button should be select one at a time | Selects only one radiobutton at a time | PASS
LY_CP_10 | Check whether the text message below razor pay radiobutton dissappear when cash on delivery cod radio button is selected | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Select cash on delivery cod radio button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | The text message below razor pay radiobutton should dissappear | The text message is dissappearing | PASS
LY_CP_11 | Check whether the text message below razor pay radiobutton appear when razorpay secure radio button is disselected | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Select razor pay radiobutton | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | The text message below razor pay radiobutton should appear | The text message is appearing | PASS
LY_CP_12 | Check whether radiobutton in billing address section can be selected only one at a time | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Select any of the radiobutton 10.Again try to select other radiobuttons | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Only one radio button should be select one at a time | Selects only one radiobutton at a time | PASS
LY_CP_13 | Check whether use a different billing address radiobutton shows other address fill dropdown if selected | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Select use a different billing address radiobutton | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Address filled dropdown should show | Address filled dropdown shows | PASS
LY_CP_14 | Check whether the other address fill dropdown dissappear when same as shipping address radiobutton is selected | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Select same as shipping address radio button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Address fill dropdown should dissappear | Address fill dropdown is dissappearing | PASS
LY_CP_15 | Check whether order summary shows when cash on delivery radio button is selected and pay now button is clicked | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Select cash on delivery cod radio button 10.Click on pay now button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Order summary page should open | Order summary is showing | PASS
LY_CP_16 | Check whether the total amount to be paid in order summary shows if cash on delivery is selected by clicking on pay now button | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Select cash on delivery cod radio button 10.Click on pay now button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Total amount to be paid should show in order summary for cash on delivery | Total amount to be paid is showing | PASS
LY_CP_17 | Check whether discount code field is working | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on discount code field | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Discount code field is working | Discount field is working | PASS
LY_CP_18 | Check whether apply button freezes when no input is in discount code field | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9..Click on apply button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Apply button should freeze when no input is written in dicount code field | Apply button freezes when no input is written in discount code field | PASS
LY_CP_19 | Check whether apply button unfreezes when there is input in discount code field | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Write input in discount code field 10.Click on apply button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Apply button should unfreeze when input is written in dicount code field | Apply button unfreezes when input is written in discount code field | PASS
LY_CP_20 | Check whether discount code field hover active function is present | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Write input in discount code field | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Discount code field hover active function should be present | Discount code field hover active function is present | PASS
LY_CP_21 | Check whether refund policy,shipping policy,privacy policy,terms of service links are working | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click refund policy link 10.Click on shipping policy link 11.Click on privacy policy link 12.Click on terms of service link | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Refund policy,shipping policy,privacy policy,terms of service links should work | Refund policy,shipping policy,privacy policy,terms of service links are working | PASS
LY_CP_22 | Check whether 3 dot icon is clicked then edit dropup appears in ship to section | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Edit dropup should appear in ship to section | Edit dropup appears in ship to section | PASS
LY_CP_23 | Check whether edit dropup can be selected in ship to section | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Edit modal should open | Edit modal is opening | PASS
LY_CP_24 | Check whether the dropdown icon in ship to section displays use a different address option with plus sign | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Use a different address option with plus sign should appear | Use a different address option with plus sign appears | PASS
LY_CP_25 | Check whether the same default address given in address page is auto filled in edit modal in ship to section by clicking on edit dropup | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Default address in address page should autofill in edit modal | Default address in address page autofills | PASS
LY_CP_26 | Verify that the edit default address process stops when cancel link in edit modal is clicked | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Click on cancel link | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | No change in address should be there | No change in address | PASS
LY_CP_27 | Verify that edited default address has updated both in checkout and address page by clicking on save button in edit modal | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Click on save button 13.Click on cart icon 14.Click on My account link 15.Click on view addresses link | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Edited default address should update in both checkout and address page | Edited default address updates in both checkout and address page | PASS
LY_CP_28 | Check whether the phone field format in edit modal is applied | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in phone number field 13.Press enter key | 2324244534 34554 | Phone number field should show alert without saving | Phone number field shows alert | PASS
LY_CP_29 | Check whether the city field in edit modal accepts only alphabetical characters | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in city field 13.Press enter key | 3445345 | City field should accept only alphabetical characters | City field accepts numerical character also | FAIL
LY_CP_30 | Check whether the city field in edit modal has character limit upto 15 | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in city field 13.Press enter key | ASBHJSDFJSDJFSJDFJSDFSDFJKSDFJKSDJKFKSDFJKSDFJKHSDFKJHSKFSDKJFGJKS | City field should accept characters upto 15 | City firld has no character limit | FAIL
LY_CP_31 | Check whether the city field in edit modal has no empty values | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Do not write any value in city field 13.Press enter key |  | City field should not accept empy values | City field doesn’t accept empty values | PASS
LY_CP_32 | Check whether the phone field in edit modal has no empty values | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Do not write any values in phone field 13.Press enter key |  | Phone field should not accept empty values | Phone field doesn’t accept empty values | PASS
LY_CP_33 | Check whether the pincode field limit in edit modal updates when country value is changed | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Select india in country field 13.Write input in pincode field 12.Press enter key | 6856089 | Pincode field limit should change according to country field value | A text message comes | PASS
LY_CP_34 | Check whether the pincode field in edit modal has no empty values | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Do not write any value in pincode field 13.Press enter key |  | Pincode field should not accept empty values | A text message appears | PASS
LY_CP_35 | Check whether the pincode field in edit modal accepts only numerical characters | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in pincode field 13.Press enter key | dgsjgjsgjhgfhg\hgfj | Pincode field should accept only numerical characters | A text message appears | PASS
LY_CP_36 | Check whether the comment box message appears when cursor is hovered on question icon in edit modal | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Place cursor on question icon | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Comment box should appear when cursor is hovered on question icon | Comment box appear | PASS
LY_CP_37 | Check whether the appartment field in edit modal has no empty values | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Do not write any values in appartment field 13.Press enter key | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Appartment field should not accept empty values | A text message appears | PASS
LY_CP_38 | Check whether the appartment field in edit modal contain minimum 3 characters | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in appartment field 13.Press enter key | as | Appartment field should have minimum 3 characters | A text message appears | FAIL
LY_CP_39 | Check whether the address field in edit modal contain minimum 3 characters | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in address field 13.Press enter key | as | Address field should have minimum 3 characters | A text message appears | FAIL
LY_CP_40 | Check whether the city field in edit modal contain minimum 3 characters | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in city field 13.Press enter key | as | City field should have minimum 3 characters | A text message appears | FAIL
LY_CP_41 | Check whether the company field in edit modal accepts empty values also | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Do not write any values in company field 13.Press enter key |  | Company field should accept empty values also | Company field also contain empty values | PASS
LY_CP_42 | Check whether the province field in address page is same as state field in edit modal | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on my account link 8.Click on view addresses 9.Click on add address 10.Select india in country field 11.Select kerala in city field 12.Click save button 13.Click on cart icon 14.Click on checkout button 15.Click on dropdown icon 15.Click on 3 dot icon 17.Click on edit dropup | Kerala | State field should be same as province field | State field is same as province field | PASS
LY_CP_43 | Check whether the state field in edit modal changes according to country field | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button | India | State field should change prior to country field | State field changes accordingly | PASS
LY_CP_44 | Check whether first name and last name field in edit modal accepts only alphabetical characters | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in first name field 13.Write input in last name field 14.Press enter key | first name=123 last name=122424 | First name field and last name field should accept only alphabetical characters | First name and last name field accepts numerical characters | FAIL
LY_CP_45 | Check whether the first name and last name field in edit modal has no empty values | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Do not write any values in first name and last name field 13.Press enter key |  | First name field and last name field should not accept empty values | First name and last name field do not accept empty values | PASS
LY_CP_46 | Check whether address field in edit modal has no empty values | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Do not write any values in address field 13.Press enter key |  | Address field should not accept empty values | Address field doesn’t accept empty values | PASS
LY_CP_47 | Check whether any of fields are empty then an alert text appears | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Do not write any values in fields 13.Press enter key |  | A text message should appear | Text message appears | PASS
LY_CP_48 | Check whether the edit modal inputs are empty in use a different address option | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on use different address option | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Edit modal inputs in use a different address option should have empty values | Edit modal in use a different address option has empty values | PASS
LY_CP_49 | Check whether the country field must contain alphabetical values when save button is clicked | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on use different address option 10.Try to change country field |  | Country field should contain only alphabetical characters | Country field restricts "---" values | PASS
LY_CP_50 | Check whether the edit modal inputs in use a different address save as next address in address page by clicking save button | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on use different address option 10.Write inputs in appropriate fields 11.Click on save button 12.Click on cart icon 13.Click on my account link 14.Click on view addresses |  | Address given in use a different address should update as next address in address page | Address in address page updates | PASS
LY_CP_51 | Check whether use a different address option becomes next radio button when save button in edit modal is clicked | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on use different address option 10.Write inputs in appropriate fields 11.Click on save button |  | Use a different address option should become next radio button | Use a different address option becomes next radio button | PASS
LY_CP_52 | Check whether if 3 dots is clicked in different address in ship to section then edit and delete options appear as dropup | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Select use a different address option 11.Write appropriate inputs in edit modal 12.Click on save button 13.Click on 3 dots | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Edit and delete dropup options should be present | Edit and delete options are present | PASS
LY_CP_53 | Check whether delete option deletes the corresponding address in use a different address in ship to section | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Select use a different address option 11.Write appropriate inputs in edit modal 12.Click on save button 13.Click on 3 dots 14.Click on delete option | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Added different address should delete from the records | Added different address deletes from the records | PASS
LY_CP_54 | Check whether the site navigates to payment gateway and verify when razorpay secure radiobutton is selected and pay now button is clicked | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write appropriate values in the fields 13.Select razorpay secure radiobutton 14.Click on pay now button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Payment gateway should open | Payment gateway is opening | PASS
LY_CP_55 | Check whether the pay now button is not functional when delivery section fields are empty and a red text alert appears corresponding to the fields | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Write appropriate values in the fields 7.Click on pay now button | https://www.lyrovo.com/ 95mswathi@gmail.com | Pay now button should continue navigation only if inputs given are valid | Pay now button continue navigation if inputs are valid | PASS
LY_CP_56 | Check whether if save the information for next time check box is selected then the delivery section field inputs are saved for the next time corresponding to given email id | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Write appropriate values in the fields 7.Check save the information checkbox 8.Repeat the steps from 1 to 7 | https://www.lyrovo.com/ 95mswathi@gmail.com | Inputs should save prior to email id given when next time checkout initiates | Inputs save in checkout page | PASS
LY_CP_57 | Check whether cancel button is given for checkout page | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Write appropriate values in the fields 7.Check save the information checkbox | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Cancel button should be present in checkout page | No cancel button is present | FAIL
LY_CP_58 | Check whether the vaild phone field format in checkout page is given without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Press enter key | 343436563 | Valid phone number format should be given in phone field | A text message is showing | PASS
LY_CP_59 | Check whether the city field in checkout page accepts only alphabetical characters without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Write city field inputs 7.Press enter key | 154 | City field in checkout page should accept only alphabetical characters without logging in | City field accepts numerical character also | FAIL
LY_CP_60 | Check whether the city field in checkout page has character limit upto 15 without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Write value in city field 7.Press enter key | hjghjagdhghdjashajgfjagjghgjhghjgjghjgjhfhhgh | City field should have character limit upto 15 | City field doesn’t have character limit | FAIL
LY_CP_61 | Check whether the city field in checkout page has no empty values without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Leave blank value in city field 7.Press enter key |  | City field should give alert text message when the field is empty | A text message is showing | PASS
LY_CP_62 | Check whether the phone field in checkout page has no empty values without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Leave blank value in phone field 7.Press enter key |  | Phone should give an alert text message when field is empty | An alert text message is showing | PASS
LY_CP_63 | Check whether the pincode field limit in checkout page updates when country value is changed without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Select india in country field 7.Write input on pincode field 8.Press enter key | India 5763727273 | Pincode field should give an alert message | An alert text message is showing | PASS
LY_CP_64 | Check whether the pincode field in checkout page has no empty values without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Select india in country field 7.Write input on pincode field 8.Press enter key | India | Pincode field should not accept empty values | Pincode field doesnot accept empty values | PASS
LY_CP_65 | Check whether the pincode field in checkout page accepts only numerical characters without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Select india in country field 7.Write input on pincode field 8.Press enter key | hghghg | Pincode field should give an alert message | An alert text message is showing | PASS
LY_CP_66 | Check whether the comment box message appears when cursor is hovered on question icon in checkout page without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Place cursor on question icon in phone field | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | A comment box should be present | Comment box appears | PASS
LY_CP_67 | Check whether the appartment field in checkout page has no empty values without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Leave a blank value in apartment field 7.Press enter key |  | Apartment field should not accept empty values | Apartment field doesn’t accept empty values | PASS
LY_CP_68 | Check whether the company field in checkout page accepts empty values also without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Leave a blank value in company field 7.Press enter key |  | Company field should accept empty values also | Company field accepts empty values | PASS
LY_CP_69 | Check whether the state field in checkout page changes according to country field without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Select india in country field 7.Click on state field | India | State field should change when country field changes | State field is changing prior to country field | PASS
LY_CP_70 | Check whether first name and last name field in checkout page accepts only alphabetical characters without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Write first name and last name inputs 7.Press enter key | 3253265 957687jh | First name and last name field in checkout page should accept only alphabetical characters without logging in | First name and last name field accepts numerical characters also | FAIL
LY_CP_71 | Check whether the first name and last name field in checkout page has no empty values without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Leave a blank value in first name and last name field 7.Press enter key |  | First name and last name field should not accept empty values | First name and last name field do not accept empty values | PASS
LY_CP_72 | Check whether address field in checkout page has no empty values without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Leave a blank value in address field 7.Press enter key |  | Address field should not accept empty values | Address field do not accept empty values | PASS
LY_CP_73 | Check whether any of fields are empty then an alert text appears without logging in checkout page | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Leave every field blank 7.Press enter key |  | Text messages prior to all fields should appear | Text message appears | PASS
LY_CP_74 | Check whether the order id is generated for each orders after payment | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write appropriate input in the fields 6.Check save this information for the next time 7.Select on razor pay secure radiobutton 8.Click on pay now button | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Order id should be generated for each and every orders | Order id is generating | PASS
LY_CP_75 | Check whether cart icon in checkout page is working | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Click on cart icon | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Cart page should open | Cart page is opening | PASS
LY_CP_76 | Check whether the email field contains email format in checkout page without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write input in email field 6.Press enter key | aghgahsgh | Email field should give an alert message | Email field shows an alert message | PASS
LY_CP_77 | Check whether the mobile phone number field contains numerical characters in checkout page without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Press enter key | efyuyufyue | Phone field should accept only numerical characters | Phone field accepts only numerical values and an alert message shows | PASS
LY_CP_78 | Check whether if any changes are made in address and if email id exist then its updated in the address page of given email id account without logging in | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write appropriate input in the fields 6.Check save this information for the next time 7.Click on cart icon 8.Click on my account link 9.Click on view addresses | add address | Address page should show saved address if the email id exist | Address page updates the address | PASS
LY_CP_79 | Check whether the login page opens when the login link in checkout page is clicked | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Click on login link | https://www.lyrovo.com/ 95mswathi@gmail.com S***** | Login page should open | Login page is opening | PASS

## Bug Report
LYROVO
OS:Windows,Browser:Chrome Version 122.0.6261.95 (Official Build) (64-bit) |  |  |  | Date:18/04/2024
Verified by:Rakhi |  |  |  | Tested by:Swathy Krishna
Bug Id | Test Id | Expected Result | Bug Description | Steps to Reproduce | Screenshot | Severity | Priority | Status
LY_BU_01 | LY_LP_03 | Lyrovo facebook profile should open by clicking on like us link | Lyrovo facebook page is not opening | 1.Open lyrovo homepage 2.Click on like us link |  | Major | Low | New
LY_BU_02 | LY_LP_05 | Message alignment should be proper | Message alignment is not proper | 1.Open lyrovo homepage 2.Write input in search field 3.Press enter key |  | Minor | Low | New
LY_BU_03 | LY_LP_07 | Categories link should include every products | Both category link and catelog link contents are same | 1.Open the lyrovo page 2.Click on categories link 3.Click on catelog link |  | Minor | Low | New
LY_BU_04 | LY_LP_16 | Wishlist page should open by clicking on wishlist link | Wishlist page is not opening | 1.Open the lyrovo page 2.Click on wishlist link |  | Major | High | New
LY_BU_05 | LY_LP_19 | My account link should appear only after logging in | My account link appears without logging in | 1.Open the lyrovo page 2.Click on login link 3.Write input in email id 4.Write input in password 5.Click on login button |  | Minor | Low | New
LY_BU_06 | LY_LP_20 | Scroll left and right icons should wrap at the edges of the image | Scroll left and right icon are not wrapped properly | 1.Open the lyrovo page |  | Enhancement | Low | New
LY_BU_07 | LY_LP_21 | Scroll left and right icons should not overlap over the buttons | Scroll left and right icon are overlapping over buttons | 1.Open the lyrovo page |  | Minor | Low | New
LY_BU_08 | LY_LP_23 | Third image link should navigate to corresponding buying pages of the product given in the images | Third image navigates to homepage | 1.Open the lyrovo page 2.Click third image link |  | Major | Low | New
LY_BU_09 | LY_LP_22 | Images given as links should not repeat | Some of the images are repeating | 1.Open the lyrovo page |  | Enhancement | Low | New
LY_BU_10 | LY_LP_28 | Products should add to wishlist before logging in | No products are adding in wishlist | 1.Open the lyrovo page 2.Select an item to add on wishlist by clicking on love icon |  | Major | High | New
LY_BU_11 | LY_LP_32 | Scroll left and right icon should not overlap over images under trending now | Scroll left and right icon are overlapping over images | 1.Open the lyrovo page |  | Enhancement | Low | New
LY_BU_12 | LY_LP_35 | Proper title should be given to the button for instagram navigation | View gallery is written on button which is misleading | 1.Open the lyrovo page |  | Trivial | High | New
LY_BU_13 | LY_LP_36 | Information title should not be there | Information title has no submodules or contents | 1.Open the lyrovo page |  | Trivial | Low | New
LY_BU_14 | LY_LP_37 | Footer menu contents should not be repeat | Submodules under footermenu are repeating | 1.Open the lyrovo page |  | Enhancement | Low | New
LY_BU_15 | LY_LP_41 | Newsletter field should be a checkbox after logging in | Newsletter field is present before logging in | 1.Open the lyrovo page 2.Click on login link 3.Write input in email id 4.Write input in password 5.Click on login button |  | Enhancement | Low | New
LY_BU_16 | LY_LP_42 | Privacy policy link under shop should open privacy policy page | Privacy policy link showing 404 error | 1.Open the lyrovo page 2.Click on support link under shops section 3.Click on privacy policy link |  | Major | Low | New
LY_BU_17 | LY_LP_44 | Like us facebook should not repeat | Unwanted like us facebook text is written on footer of page | 1.Open the lyrovo page |  | Trivial | Low | New
LY_BU_18 | LP_LO_06 | Create an account button hover active colour fill should be black | Create an account button hover active colour fill is white | 1.Open the lyrovo page 2.Click on login link 3.Place mouse on create an account button |  | Trivial | High | New
LY_BU_19 | LP_LO_10 | An alert message showing fill the above fields should show in login modal | No alert message is showing | 1.Open the lyrovo page 2.Click on login link 3.Click on login button |  | Major | High | New
LY_BU_20 | LP_LO_13 | Password eye icon field should be present | Password eye icon field is not present | 1.Open the lyrovo page 2.Click on login link 3.Click on login button |  | Enhancement | High | New
LY_BU_21 | LP_LO_18 | A toast message should appear when email field is incomplete and password field is clicked | Toast message is not showing | 1.Open the lyrovo page 2.Click on login link 3.Write input in email address field 4.Click on password field |  | Minor | High | New
LY_BU_22 | LP_LO_19 | Email id field should restrict characters after 64 | Email id field is not restricting | 1.Open the lyrovo page 2.Click on login link 3.Write input in email address field |  | Enhancement | Low | New
LY_BU_23 | LP_LO_21 | Password field cursor should be active when enter key is clicked and email field is inputted | Login page loads when enter key is pressed | 1.Open the lyrovo page 2.Click on login link 3.Write input in email address field 4.Press enter key |  | Enhancement | Low | New
LY_BU_24 | LP_LO_22 | An alert box showing Please enter the email and password should show | No alert box is shown | 1.Open the lyrovo page 2.Click on login link 3.Click on email address field 4.Press enter key 4.Click on password field 5.Press enter key |  | Enhancement | High | New
LY_BU_25 | LP_LO_26 | An alert box containing this email id doesnot exist should show in login page | No alert box is shown | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button |  | Enhancement | Low | New
LY_BU_26 | LP_LO_31 | Password eye icon field should be present in recover page next to password field | No password eye icon is present | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password |  | Enhancement | High | New
LY_BU_27 | LP_LO_32 | Password eye icon field should be present next to confirm password field in recover page | No password eye icon is present | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password |  | Enhancement | High | New
LY_BU_28 | LP_LO_36 | Login page should open when password has been reset | Account page is opening | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 8.Write input in password field 9.Write input in password field 10.Click on submit button |  | Major | High | New
LY_BU_29 | LP_LO_37 | A text message should show if the new password entered is same as current password | Its not showing text message | 1.Open the lyrovo page 2.Click on login link 3.Click on forgot your password link 4.Write input in email field 5.Click on submit button 6.Open mail 7.Click on reset your password 8.Write input in password field 9.Press enter key |  | Enhancement | High | New
LY_BU_30 | LP_LO_41 | An alert box showing this mail id doesn’t exist should show in login modal | No alert box is shown | 1.Open the lyrovo page 2.Click on login link 3.Click on email address field 4.Press enter key 4.Click on password field 5.Press enter key 6.Click on login button |  | Enhancement | Low | New
LY_BU_31 | LY_RP_01 | Toast message containing first name field must contain only alphabetical characters should show | First name field accepts every character | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key |  | Major | High | New
LY_BU_32 | LY_RP_02 | Toast message containing first name field must have atleast 5 characters should show | First name field accepts less than 5 characters | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key |  | Enhancement | Low | New
LY_BU_33 | LY_RP_03 | Toast message containing this field must have maximum 15 characters should show | First name character field limit is more than 15 | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key |  | Enhancement | Low | New
LY_BU_34 | LY_RP_04 | First name field should automatically convert first word to uppercase | First name field is not converting to uppercase | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key |  | Enhancement | Low | New
LY_BU_35 | LY_RP_05 | First name field should accept only one space character | First name field contains more than one space character | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key |  | Enhancement | Low | New
LY_BU_36 | LY_RP_06 | First name field first character should not be a space character | First name field accepts first character as space | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key |  | Minor | Low | New
LY_BU_37 | LY_RP_07 | Cursor should move to last name field if first name field is complete | Its doesn’t move to last name field | 1.Open the lyrovo page 2.Click on register link 3.Write input in first name field 4.Press enter key |  | Minor | Low | New
LY_BU_38 | LY_RP_08 | Toast message containing first name field cannot be empty should show | First name field accepts empty values | 1.Open the lyrovo page 2.Click on register link 3.Click on last name field |  | Major | High | New
LY_BU_39 | LY_RP_09 | Last name field should accept only alphabetical characters | Last name field accepts every type of characters | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key |  | Major | High | New
LY_BU_40 | LY_RP_10 | Last name should accept minimum 5 characters | Last name field accepts less than 5 characters | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key |  | Enhancement | Low | New
LY_BU_41 | LY_RP_11 | Last name field should accept characters upto 15 | Last name field has no limitation | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key |  | Enhancement | Low | New
LY_BU_42 | LY_RP_12 | Last name field should change first characeter to uppercase | Last name field doent change first characetr to uppercase | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key |  | Enhancement | Low | New
LY_BU_43 | LY_RP_13 | Last name field should accept only one space character | Last name field accept more than one space character | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key |  | Enhancement | Low | New
LY_BU_44 | LY_RP_14 | Last name field first character should not be a space character | Last name field character accepts first character as space | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key |  | Minor | High | New
LY_BU_45 | LY_RP_15 | Cursor should move to email address field if last name field is complete | Cursor doesn’t move to email address field | 1.Open the lyrovo page 2.Click on register link 3.Write input in last name field 4.Press enter key |  | Minor | Low | New
LY_BU_46 | LY_RP_16 | Toast message should show when last name field is empty | Last name field accepts empty values also | 1.Open the lyrovo page 2.Click on register link 3.Place cursor n email address field |  | Major | High | New
LY_BU_47 | LY_RP_20 | Password eye icon should be present next to password field in register page | Password eye icon is not present | 1.Open the lyrovo page 2.Click on register link |  | Minor | High | New
LY_BU_48 | LY_RP_24 | A message showing account created successfully should show and login page should open when new account is created | No message is shown and my account page is opening | 1.Open the lyrovo page 2.Click on register link 3.Write appropriate input in the fields |  | Major | Low | New
LY_BU_49 | LY_RP_25 | Mobile number field should be present in register page | Mobile number field is not present | 1.Open the lyrovo page 2.Click on register link |  | Minor | High | New
LY_BU_50 | LY_RP_26 | Email verification field should be present in register page | Email verification field is not present | 1.Open the lyrovo page 2.Click on register link |  | Minor | High | New
LY_BU_51 | LY_RP_27 | Confirm password field should be present | Confirm password field is not present | 1.Open the lyrovo page 2.Click on register link |  | Minor | Low | New
LY_BU_52 | LY_UP_01 | Wishlist page should open | Wishlist page is not opening | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on wishlist icon |  | Major | High | New
LY_BU_53 | LY_UP_02 | User name should appear as link next to logout link | My account link is next to logout link | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button |  | Enhancement | Low | New
LY_BU_54 | LY_UP_09 | First name field should accept only alphabetical characters | First name field contains other characters also | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key |  | Major | High | New
LY_BU_55 | LY_UP_10 | First name field should accept only one space character | First name field contains other characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key |  | Minor | Low | New
LY_BU_56 | LY_UP_11 | First name field should accept characters upto 15 | First name field contains more than 15 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key |  | Enhancement | Low | New
LY_BU_57 | LY_UP_12 | First name field should change first character to uppercase | First name field doesn’t change first character to uppercase | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key |  | Enhancement | Low | New
LY_BU_58 | LY_UP_13 | First name field should not accept empty values | First name field contains empty value also | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key |  | Major | Low | New
LY_BU_59 | LY_UP_14 | First name field should not accept less than 3 characters | First name field has no limit | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in first name field 8.Press enter key |  | Enhancement | Low | New
LY_BU_60 | LY_UP_15 | Last name field should accept only alphabetical characters | Last name field contains other characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key |  | Major | High | New
LY_BU_61 | LY_UP_16 | Last name field should accept only one space character | Last name field contains other characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key |  | Minor | Low | New
LY_BU_62 | LY_UP_17 | Last name field should accept characters upto 15 | Last name field contains more than 15 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key |  | Enhancement | Low | New
LY_BU_63 | LY_UP_18 | Last name field should change first character to uppercase | Last name field doesn’t change first character to uppercase | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key |  | Enhancement | Low | New
LY_BU_64 | LY_UP_19 | Last name field should not accept empty values | Last name field contains empty value also | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key |  | Minor | Low | New
LY_BU_65 | LY_UP_20 | Last name field should not accept less than 3 characters | Last name field has no limit | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in last name field 8.Press enter key |  | Enhancement | Low | New
LY_BU_66 | LY_UP_21 | Company field should accept characters only upto 30 in address page | Company field has no limit | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in company field 8.Press enter key |  | Enhancement | Low | New
LY_BU_67 | LY_UP_22 | Company field should conatin only numerical and alphabetical characters | Company field accepts every type of character | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in company field 8.Press enter key |  | Enhancement | Low | New
LY_BU_68 | LY_UP_25 | Address 1 field should not accept empty values | Address1 field accepts empty values | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address1 field 8.Press enter key |  | Minor | Low | New
LY_BU_69 | LY_UP_26 | Address 1 field should contain only numerical ad alphabetical characters | Address 1 field accepts every type of characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address1 field 8.Press enter key |  | Enhancement | Low | New
LY_BU_70 | LY_UP_27 | Address 2 field should contain only numerical and alphabetical characters | Address 2 field accepts every type of characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address 2 field 8.Press enter key |  | Enhancement | Low | New
LY_BU_71 | LY_UP_28 | Address 1 field should contain characters upto 100 | Address 1 field contain more than 100 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address 1 field 8.Press enter key |  | Enhancement | Low | New
LY_BU_72 | LY_UP_29 | Address 2 field should contain characters upto 100 | Address2 field contain more than 100 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in address2 field 8.Press enter key |  | Enhancement | Low | New
LY_BU_73 | LY_UP_30 | City field should accept characters upto 20 | City field accepts more than 20 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in city field 8.Press enter key |  | Minor | Low | New
LY_BU_74 | LY_UP_31 | City field should accept only alphabetical characters | City field accepts every type of characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in city field 8.Press enter key |  | Minor | Low | New
LY_BU_75 | LY_UP_32 | City field should contain minimum 3 characters | City field accept less than 3 characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in city field 8.Press enter key |  | Enhancement | Low | New
LY_BU_76 | LY_UP_33 | City field should not accept empty values | City field accepts empty values | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in city field 8.Press enter key |  | Major | High | New
LY_BU_77 | LY_UP_35 | Country field default value should be "---" | Country field default is not "---" | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address |  | Enhancement | Low | New
LY_BU_78 | LY_UP_38 | Default value in province field should be "---" | No default value is present for province field | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select india in country field |  | Enhancement | Low | New
LY_BU_79 | LY_UP_40 | Country field should not accept empty values | Country field accepts empty values | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select "---" in country field |  | Major | Low | New
LY_BU_80 | LY_UP_41 | Province field should not accept empty values | Province field accepts empty value | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select india in country field 8.Select "---" in province field |  | Major | Low | New
LY_BU_81 | LY_UP_42 | Postal code field should accept only numerical characters | Postal code field accepts every type of characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in postal code field 8.Press enter key |  | Major | Low | New
LY_BU_82 | LY_UP_43 | Phone number field should accept only numerical characters | Phone number field accepts every type of characters | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Write input in phone number field 8.Press enter key |  | Major | Low | New
LY_BU_83 | LY_UP_44 | Phone field should accept only 10 numerical characters if country value is india | Phone field has no limit | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on view addresses 6.Click on add new address 7.Select india in country value 8.Write input in phone field 9.Press enter key |  | Minor | High | New
LY_BU_84 | LY_UP_49 | A text message should appear containing all fields are mandatory without adding the address | Text containing only password and email address field is mandatory is showing | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Write appropriate values in fields 6.Click on add address button 7.Write appropriate inputs in the fields 8.Press enter key |  | Major | High | New
LY_BU_85 | LY_CP_06 | Shipping charge should add if total amount is below 800 | Shipping charge does not add for amount below 800 | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button |  | Major | High | New
LY_BU_86 | LY_CP_29 | City field should accept only alphabetical characters | City field accepts numerical character also | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in city field 13.Press enter key |  | Major | Low | New
LY_BU_87 | LY_CP_30 | City field should accept characters upto 15 | City firld has no character limit | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in city field 13.Press enter key |  | Enhancement | Low | New
LY_BU_88 | LY_CP_38 | Appartment field should have minimum 3 characters | A text message appears | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in appartment field 13.Press enter key |  | Enhancement | Low | New
LY_BU_89 | LY_CP_39 | Address field should have minimum 3 characters | A text message appears | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in address field 13.Press enter key |  | Enhancement | Low | New
LY_BU_90 | LY_CP_40 | City field should have minimum 3 characters | A text message appears | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in city field 13.Press enter key |  | Enhancement | Low | New
LY_BU_91 | LY_CP_44 | First name field and last name field should accept only alphabetical characters | First name and last name field accepts numerical characters | 1.Open the lyrovo page 2.Add an item to cart 3.Click on login link 4.Write input in email address 5.Write input in password 6.Click on login button 7.Click on cart 8.Click on checkout button 9.Click on dropdown icon 10.Click on 3 dot icon 11.Click on edit dropup 12.Write input in first name field 13.Write input in last name field 14.Press enter key |  | Major | Low | New
LY_BU_92 | LY_CP_57 | Cancel button should be present in checkout page | No cancel button is present | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Write appropriate values in the fields 7.Check save the information checkbox |  | Enhancement | lLow | New
LY_BU_93 | LY_CP_59 | City field in checkout page should accept only alphabetical characters without logging in | City field accepts numerical character also | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Write city field inputs 7.Press enter key |  | Minor | High | New
LY_BU_94 | LY_CP_70 | First name and last name field in checkout page should accept only alphabetical characters without logging in | First name and last name field accepts numerical characters also | 1.Open the lyrovo page 2.Add an item to cart 3.Click on cart 4.Click on checkout button 5.Write email/phone number in contact field 6.Write first name and last name inputs 7.Press enter key |  | Major | High | New
LY_BU_95 | LY_UP_52 | Spin box value should accept values above 1 | Spin box value accept negative and 0 numbers | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on cart icon 6.Click on down button in spin box |  | Major | High | New
LY_BU_96 | LY_UP_53 | Cart page should have empty cart item | Cart page is not working | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on cart icon 6.Click on down button in spin box 7Click on view cart button |  | Major | High | New
LY_BU_97 | LY_UP_54 | Item per page should show 12 products in the catelog page | Item per page is not working | 1.Open the lyrovo page 2.Write input in email address 3.Write input in password 4.Click on login button 5.Click on catelog link 6.Select numbers in item per page |  | Minor | Low | New
New
New
New
New
New
New
New
New
New

## Defect Distribution Graph
DEFECT DISTRIBUTION GRAPH
MODULES NAME | DEFECT DISTRIBUTION
Home Page | 17
Login Page | 13
Registration Page | 21
User profile page | 36
Checkout and Payment | 11

## Test Report
SL.NO | MODULE NAME | TESTCASE PASSED | TESTCASE FAILED | TOTAL TESTCASE
1 | Home Page | 27 | 17 | 44
2 | Login Page | 13 | 13 | 41
3 | Registration Page | 8 | 21 | 29
4 | User Profile Page | 18 | 36 | 54
5 | Checkout and Payment | 68 | 11 | 79